## Notes
Topic | Task | Description | Notes
Competitors | 1. Perform Competitive Intelligence | 1. Review websites of similar companies/products in our space | Here are the top competitors you should start looking at:
|  | 2. As time allows, Download, install and try the various products or go through the demos and videos, as available. | Industry veterans: Alteryx Rapid Miner Lavastorm Pipeline Pilot
|  | 3. Get a feel for how their users use their products and what features are common across all of these or unique; get ideas for UX redesign of our system | New Web-based systems: StreamSets mendix pneuron AzureML
Competitors with strong focus on data viz: Tibco Spotfire Pentaho Tableau
Product Design | 1. Design Guide: colors, fonts, icons, … across the product
2. UX redsign
| a. Sign-In page |  | Should be big and easy to register and/or sign on right away: https://plot.ly/ does this well.
| b. Designer (App authoring tool) |  | Get ideas from our competitors on where to place the module palette, design tools (e.g., undo/redo features), help documentation, etc.
| c. Discovery page |  | Move towards a block masonary grid. Nice flat minimal design; hover over exposes buttons to choose the app, etc. Something like pinterest…
| d. Dashboards |  | This will be a whole project in and of itself, and will be a multi-person effort…

## ProjectPlan
Actual (beyond plan)
ACTIVITY | START | DURATION | PERIODS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Competitive Intelligence, Ramp Up | 1 | 1
Design Guide | 1 | 2
Wireframes
a. Sign-In page | 3 | 1
b. Designer (App authoring tool) | 4 | 1
c. Discovery page | 5 | 1
d. Dashboards | 6 | 1
Implementation
a. Sign-In page | 7 | 2
b. Designer (App authoring tool) | 9 | 2
c. Discovery page | 11 | 2
d. Dashboards | 13 | 2